## SUMMARY
2018/19 MID-YEAR PERFORMANCE SUMMARY:
The tabulation below illustrates that the overal mid-year performance of the municipality for financial year 2018/2019 is 91%. Calculation of Mid-year Achievement was based the overall achievement of targets by 30 December 2018 as supported by evidence made available for the purposes of this report.
OFFICE /CLUSTER | TOTAL TARGETS PLANNED | TOTAL TARGETS ACHIEVED | VARIANCE | PERCENTAGE (%) MID-YEAR ACHIEVEMENTS 2018/2019
Office of the Municipal Manager | 9 | 8 | 1 | 88.89%
Finance | 13 | 11 | 2 | 84.62%
Corporate Services | 19 | 18 | 1 | 94.74%
Community Services | 11 | 11 | 0 | 100%
Transport, Infrastructure & Environment & Licensing | 12 | 11 | 1 | 91.67%
Strategic Planning & Local Economic Development | 17 | 15 | 2 | 88.24%
TOTAL | 81 | 74 | 7 | 91.36%
Reviewed and Verified by:
Ms. S. Mpeta
Director: Office of the Municpal Mnager

## MM's Office
SEDIBENG DISTRICT MUNICIPALITY
OFFICE OF THE MUNICIPAL MANAGER
PERFORMANCE REPORTING FOR 2018/19 FINANCIAL YEAR
Priority Area | IDP Strategy | IDP Objective | Objective No. | Key Performance Indicator (KPI) | KPI No | Baseline | Budget Amount | Funding Source | Annual Target | Quarter One(1) | Achieved /Not Achieved | Reason for Non, under/Over Achievement | Corrective Action | POE Obtained | Mainstreaming Designated (Yes/No) |  | PMS Comments | Internal Audit Comments | Quarter Two(2) | Achieved /Not Achieved | Reason for Non, under/Over Achievement | Corrective Action | POE Obtained | Mainstreaming Designated (Yes/No) |  | PMS Comments
[15 empty] | (Yes/No) | Group F/M/Y/E/D | [7 empty] | (Yes/No) | Group F/M/Y/E/D
KPA1: GOOD GOVERNANCE AND PUBLIC PARTICIPATION
IGR AND RISK MANAGEMENT
Inter-govermental Relations (IGR) | To facilitate co-operative government through communication, consultation and joint decision making | To promote co-operative government | D1 | Number of IGR Forums coordinated | D1.1 | Seven (7) IGR Forums coordinated in the previous financial year | 792711 | OPEX | Co-ordinate two IGR Forums | Co-ordinate (1) one IGR Forum Meeting | Not Achieved | Non availability of the members due to various reasons, i.e. National and other Provincial Interventions at ELM | Target to be implemented in Q2 | N/A | N/A | N/A | N/A | Target not Achieved.Due to poor planning and lack of compliance. | _ | Co-ordinate (1) one IGR Forum Meeting | Achieved | N/A | N/A | N/A | N/A | Satisfactory Evidence a
Risk Management | To Assess, Identify, control and monitor the implementation of mitigation measures | To ensure that the municipality's risk and risk exposures are properly managed in order to minimize uncertainty and maximize business opportunities. | D2 | Number of Risk Management Plans developed | D2.1 | 2017/2018 Risk Management Plan | 50000 | OPEX | Develop one (1) 2018/19 Risk Management Plan and submit to Risk Management Committee for Approval | Develop one (1) 2018/19 Risk Management Plan and submit to Risk Management Committee for Approval | Achieved | N/A | N/A | Risk Management Plan 18_19 | N/A | N/A | Information Verified | Information Verified. | _ | N/A | N/A | N/A | N/A | N/A | N/A | N/A
|  |  |  | Number of Risk Assessments Conducted | D2.2 | 2017/2018 Risk Registers |  |  | Conduct One (1) Annual Strategic Risk Assessment and Report | Conduct one (1) Strategic Risk Assessent and report | Achieved | N/A | N/A | Strategic Risk Register 18_19 | N/A | N/A | Information Verified | Information Verified. | _ | N/A | N/A | N/A | N/A | N/A | N/A | N/A
INTERNALAUDIT
Audit Plan | Develop, implement and monitor Risk-based Internal Audit Coverage Plan | To provide reasonable assurance and independent opinions to management and council | D3 | Number of Internal Audit Coverage Plans Developed | D3.1 | 2017/2018 Audit Plan | 1580500 | OPEX | Develop one (1) Risk-Based Internal Audit Coverage Plan | Develop one (1) Risk-Based Internal Audit Coverage Plan | Not Achieved | The plan is in draft. The Approval of the plan was postponed during the audit committee meeting | The plan will be submitted in the next Audit Committee meeting for approval | N/A | N/A | N/A | N/A | Target not Achieved. | - | Not Achived | The plan was submitted in the AC Meeting however, the discussions of the management letter took longer than anticipated and the item was deffered to the next meeting | To submit in the next meeting | N/A | N/A | N/A | N/A
SERVICE DELIVERY AND BUDGET IMPLEMENTATION PLAN
SDBIP | Ensure measurable performance and transparent monitoring of the municipal performance. | To ensure Good Governance; Sound and Accountable Management practices | D4 | Number of Service Delivery and Budget Implementation Plans(SDBIP) approved | D4.1 | Development of SDBIP | Internal | OPEX | Develop 1 (one)2019/20 SDBIP | _ | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | _ | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PERFOMANCE MANAGEMENT
PMS | Co-ordinate Performance Reporting, Monitoring and Evaluation | To promote a culture of accountability | D5 | Number of Performance Management Reports Produced | D5.1 | Performance monitoring and evaluation | 1865679 | OPEX | Monitor and evaluate 2018/19 municipal performance and produce Four (4) Reports | Monitor and evaluate quarter one (1) performance information and report | Achieved | N/A | N/A | Q1 Performance Management Report | N/A | N/A | Information Verified | Information Verified Sattisfactory. POE submmited sufficient. | Monitor and evaluate mid-year performance information and report | Achieved | N/A | N/A | N/A | N/A | N/A | Satisfactory Evidence a
GOOD GOVERNANCE& QUALITY ASSURANCE
Quality Assurance | Ensure necessary actions are taken against all findings raised by the Auditor General | To promote a culture of accountability | D6 | Percentage of Auditor General findings resolved | D6.1 | Development and Implementation of Audit Action Plan | 16082698 | OPEX | Address 90% Auditor General Findings | _ | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | _ | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Co-ordinate Municipal Reporting | To ensure clean accountable and transparent governance | D7 | Number of Annual Reports submitted to Auditor General and Council | D7.1 | 2017/18 Annual Report |  |  | Develop and Submit 2017/18 Annual Report to council | Develop and Submit Draft 2017/18 Annual Report to Council | Achieved | N/A | N/A | Council Resolution | N/A | N/A | Information Verified | Information Verified Sattisfactory. POE submmited sufficient. | _ | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LEGAL SERVICES
Contract Management | Oversee the implementation of contract management by clusters | To provide legal advice to management and council | D9 | Number of contract management oversight reports produced | D9.1 | Four Contract management oversight reports in 2017/18 financial year |  |  | Oversee the implementation of contract management and report quarterly | Oversee the implementation of contract management and report | Achieved | NA | NA | Contact Managenet Report and Attendance Register of Contract Managenent Review meetings | N/A | N/A |  | Information Verified Sattisfactory. POE submmited sufficient. | Oversee the implementation of contract management and report | Achieved | N/A | N/A | Contact Managenet Report and Attendance Register of Contract Managenent Review meetings | N/A | N/A
MID-YEAR PERFORMANCE SUMMARY 2018_19
Total Mid-year Targets |  | 9
Targets Achieved |  | 8
Total Achievenet |  | 89%

## Finance
SEDIBENG DISTRICT MUNICIPALITY
FINANCE CLUSTER - CUSTODIAN: CHIEF FINANCIAL OFFICER
PERFORMANCE REPORTING FOR 2018/19 FINANCIAL YEAR
Priority Area | IDP Strategy | IDP Objective | Objective No. | Key Performance Indicator (KPI) | KPI No: | Baseline | Budget Amount | Funding Source | Annual Target | Quarter One(1) | Achieved /Not Achieved | Reason for Non, under/Over Achievement | Corrective Action | POE Obtained | Mainstreaming Designated (Yes/No) |  | PMS Comments | Internal Audit Comments | Quarter Two(2) | Achieved /Not Achieved | Reason for Non, under/Over Achievement | Corrective Action | POE Obtained | Mainstreaming Designated (Yes/No) |  | PMS Comments
KPA 2: MUNICIPAL FINANCIAL VIABILITY AND MANAGEMENT
OFFICE OF THE CHIEF FINANCIAL OFFICER
Implementation of MSCOA reforms | Progressive Compliance with MSCOA regulations | To ensure successful implementation of the MSCOA regulations | F1 | Percentage of transacting on MSCOA posting accounts | F1.1 | New Target | 1500000 | OPEX | Implement 100% of MSCOA Regulations on account posting of transactions | Implement 100% of MSCOA Regulations on account posting of transactions | Achieved | n/a | n/a | General posting ledger | n/a | n/a | Information Verified | Information Verified Sattisfactory. POE submmited sufficient. | Implement 100% of MSCOA Regulations on account posting of transactions | Achieved | n/a | n/a | Provincial report and General posting ledger | n/a | n/a | Satisfactory Evidencea
FINANCIAL MANAGEMENT AND BUDGETS
Municipal budget | Compile a realistic and funded budget | To provide a realistic financial planning of the municipality | F2 | Number of municipal budgets approved | F2.1 | One (1) annual municipal budget in the previous financial | 28982018 | OPEX | Compile one (01) annual budget and submit to Council for approval | _ |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | _ | N/A | N/A | N/A | N/A | n/a | n/a | N/A
Procurement Plan | Development of an annual Procurement Plan | To determine procurement requirements and timeframes | F3 | Number of Procurement plans submitted to National Treasury | F3.1 | One (01) annual Capex Procurement plan submitted to National Treasury in the previous financial year |  |  | Develop (1) one Annual Procurement Plan | Develop (1) one Annual Procurement Plan | Achieved | NA | NA | Procurement Plan | N/A | N/A | Information Verified | Information Verified Sattisfactory. POE submmited sufficient. | _ | N/A | N/A | N/A | N/A | n/a | n/a | Satisfactory Evidencea
Cost Containment | Implement Cost Containment Strategy | To promote sound financial administration practices | F4 | Percentage of cost saving realised | F4.1 | 5% cost saving realized in the previous financial year |  |  | Realise 1% of total annual saving on operating budget within general expenses and produce four reports | Realise 1% of total Q1 saving on operating budget within general expenses and produce four reports | Achieved | NA | NA | Report and Statement of Comparison of Budget and Actual Amounts (controllable items / general expenses) | N/A | N/A | Information Verified | Information Verified Sattisfactory. POE submmited sufficient. | Realise 1% of total Q2 saving on operating budget within general expenses and produce four reports | Achieved | NA | NA | Report and Statement of Comparison of Budget and Actual Amounts (controllable items / general expenses) | n/a | n/a | Satisfactory Evidencea
Municipal Tariffs | Review tariff structure and income generating tariffs | To review the effectiveness of the existing tariff structures and the need to for restructuring | F5 | Number of municipal tariff reviews conducted | F5.1 | One (1) Review of tariff structures conducted in the previous financial year |  |  | Review tariffs for the 2019/20 financial year and submit to Council for approval | _ | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | _ | N/A | N/A | N/A | N/A | n/a | n/a | N/A
SUPPLY CHAIN MANAGEMENT
GEYODI Compliance | Monitor adherence to GEYODI | To adhere to GEYODI requirements | F6 | Percentage of jobs awarded to people with disability | F6.1 | 2% jobs awarded to people with disabilities on the previous financial year | 3360588 | OPEX | 1% of total annual jobs awarded and services rendered by people with disabilities and produce one report | 1% of total quarterly jobs awarded and services rendered by people with disabilities and produce one report | Not achieved | Lack of response from disabled people | More invitations to be sent to disabled people for quations | TER Spreadsheet |  |  | Target not Achieved | Target not Achieved | 1% of total quarterly jobs awarded and services rendered by people with disabilities and produce one report | Target not Achieved | Achieved average of 0.8%. Disabled people not responding to request for quotation | Achieved average of 0.8%. Disabled people not responding to request for quotation | Report and TER Spreadsheet | Yes | PWD | Satisfactory Evidencea
|  |  |  | Percentage of jobs awarded to women owned businesses | F6.2 | 40% jobs awarded to women owned businesses in the previous financial year |  |  | 10% of total annual jobs awarded and services rendered by women and produce one report | 10% of total quarterly jobs awarded and services rendered by womenand produce one report | Achieved | n/a | n/a | TER Spreadsheet |  |  | Information Verified | Information Verified Sattisfactory. POE submmited sufficient. | 10% of total quarterly jobs awarded and services rendered by women and produce one report | Achieved | n/a | n/a | Report and TER Spreadsheet | Yes | SMMEs | Satisfactory Evidencea
|  |  |  | Percentage (%) of jobs awarded to Youth owned businesses to date | Equitable Share | Increased number of jobs awarded to youth owned businesses |  |  | 4% of total annual jobs awarded and services rendered by youth and produce one report | 4% of total quarter 1 jobs awarded and services rendered by youth and produce one report | Achieved | N/A | N/A | Report and TER Spreadsheet |  |  | Information Verified | Information Verified Sattisfactory. POE submmited sufficient. | 4% of total quarter 2 jobs awarded and services rendered by youth and produce one report | Achieved | N/A | N/A | Report and TER Spreadsheet | Yes | Women | information verified
|  |  |  | Percentage of jobs awarded tolocal SMME's and Co-ops | F6.4 | 40% jobs awarded to local SMME's and Co-ops in the previous financial year |  |  | 30% of total annual jobs awarded and services rendered by SMMEs and Cooperatives and produce one report | 30% of total quarterly jobs awarded and services rendered by SMMEs and Cooperatives and produce one report | Achieved | n/a | n/a | TER Spreadsheet | N/A | N/A | Information Verified |  | 30% of total quaerterly jobs awarded and services rendered by SMMEs and Cooperatives and produce one report | Achieved | n/a | n/a | Report and TER Spreadsheet | N/A | N/A | Finance department should have / review the criteria of which the service providers are selected on the database. The drastic increase on trend of achievement is can be a cause for concern.
Targets Achieved |  | 11
Percentage Achievement |  | 85%

## Corporate Services
SEDIBENG DISTRICT MUNICIPALITY
CORPORATE SERVICES CLUSTER - CUSTODIAN - EXECUTIVE DIRECTOR
PERFORMANCE REPORTING FOR 2018/19FINANCIAL YEAR
Priority Area | IDP Strategy | IDP Objective | Objective No: | Key Performance Indicator (KPI) | KPI No: | Baseline | Budget Amount | Funding Source | Annual Target | Quarter One(1) | Achieved /Not Achieved | Reason for Non, under/over Achievement | Corrective Action |  | Mainstreaming Designated (Yes/No) |  | PMS Comments | Internal Audit Comments | Quarter Two(2) | Achieved /Not Achieved | Reason for Non, under/Over Achievement | Corrective Action | POE Obtained | Mainstreaming Designated (Yes/No) |  | PMS Comments
[14 empty] | POE Obtained | (Yes/No) | Group F/M/Y/E/D | [7 empty] | (Yes/No) | Group F/M/Y/E/D
KPA 5: MUNICIPAL TRANSFORMATION AND ORGANISATIONAL DEVELOPMENT
INFORMATION TECHNOLOGY
ICT Steering Committee | Ensure functionality of the ICT Steering Committee | To provide oversight to ICT operations | I1 | Percentage (%) of implementation of resolutions ICT Steering Committee | I1.1 | Previous reports of ICT Steering Committee meetings are available | 26055864 | OPEX | Implement 60% of resolutions taken by ICT Steering Committee | Implement 60% of resolutions taken by ICT Steering Committee | Achieved | N/A | N/A | See Report on Resolution Tracking Tool for the ICT Operational Steering Committee (Q1 2018).pdf | Yes | F/M/Y/E | Information Verified | Information Verified Sattisfactory.Signed Report submmitted, However the report does not have date. | Implement 60% of resolutions taken by ICT Steering Committee | Achieved | N/A | N/A | N/A | N/A | N/A | Satisfactory evidence a
Optic Fibre Project | To maintain and monitor Optic Fibre functionality | To ensure effective coverage of optic fibre | I2 | Number of functional Wi-Fi Hotspots covered by the Optic Fibre. | I2.2 | Previous report on the Optic Fibre Usage and Maintenance |  |  | Four (4) reports on Optic Fibre Functionality submitted to council | One report on Optic Fibre Functionality submitted to council | Achieved | N/A | N/A | See Report on IT Fibre Optic Performance (Q1 2018 2019).pdf | Yes | F/M/Y/E | Information Verified | Information Verified Sattisfactory.Signed Report submmitted, However the report does not have date. | One report on Optic Fibre Functionality submitted to council | Achieved | N/A | N/A | See Report on IT Fibre Optic Performance (Q2 2018 2019).pdf | Yes | F/M/Y/E/D | Satisfactory evidence a
ICT Shared services | Share ICT services with Local Municipalities | To manage ICT-related shared Service level agreements | I3 | Number of Local Municipalities utilising Sedibeng’s ICT services | I3.1 | Previous Minutes of the ICT Steering Committee |  |  | Two reports on implementation ICT Shared Sercices submitted to ICT Steering Committee | _ | Achieved | N/A | N/A | See Report on ICT Shared Services (Q1 2018 219).pdf | Yes | F/M/Y/E | N/A | N/A | One report on implementation ICT Shared Sercices submitted to ICT Steering Committee | Achived | N/A | N/A | See Report on ICT Shared Services (Q2 2018 219).pdf | Yes | F/M/Y/E/D | Satisfactory evidence a
HUMAN RESOUURCES
Skills Development Plan | To review employees’ Skills and development Training Plan and submit Annual Training Report to LGSETA | To ensure effective and competent staff | I4 | Amount of funds secured for Skills development Plan | I4.1 | Previously Approved Skills Development and Training Plan | 8440437 | OPEX | Develop one Skills Development and Training plan . | _ | N/A | N/A | N/A | N/A | N/A | N/A | Not Achieved | Target not Achieved. | _ | N/A | N/A | N/A | N/A | N/A | N/A | N/A
|  |  |  | Number of Non-PDP training programmes provided to employees | I4.2 | 2017/2018 Skills Development Training Plan |  | SETAs | Provide Non-PDP Programmed to 40 employees | _ | N/A | N/A | N/A | N/A | N/A | N/A | Not Achieved |  | Provide training non PDP training to 20 employees | Achieved | N/A | N/A | Attance register of employees who attended Disaster Management course | Yes | F/M/Y | Satisfactory evidence a
CPMD Course |  |  |  | Number of Senior and Middle management received CPMD training | I4.3 | 15 employees attained CPMD qualification |  | SETAs and other grants | Provide training for two (2) Senior and Middle Management members on Municipal Finance Management Programme | Enroll two (2) managers on Municipal Finance Management Programme | Not Achived | Application for registration with Wits University. | N/A | N/A |  |  | Not Achieved | Target not Achieved. | _ | Target still not Achieved. Wits University postponed the intake periond | N/A | N/A | N/A | N/A | N/A | N/A
Local Labour Forum | To conduct monthly LLF meetings to deliberate on issues affecting employees and management | To promote good labour relations | I5 | Percentage of implementation of LLF meetings resolutions | I5.1 | Collective Agreement is available |  | OPEX | 40% Implementation of the LLF Resolutions | 40% Implementation of the LLF Resolutions | Achived | N/A | N/A | LLF Minutes & Attendance Registers. |  |  | Information Verified | Information Verified Sattisfactory. | 40% Implementation of the LLF Resolutions | Achieved | N/A | N/A | LLF Minutes & Attendance Registers. | Yes | F/M/Y/E/D | Information verified
COUNCIL SECRETARIAT SERVICES
Method used to record, minute and file Council sitting activities | Provide secretariat services to council and its committees | Provide administrative support to council and its committees | I6 | Number of updated council resolution registers monitored | I6.1 | A new target | 12853688 | OPEX | Update 1council resolution register and monitor implementation | Update 1 council resolution register and monitor implementation | Achived | N/A | N/A | (1) one updated council resolution register | Yes | F/M/Y/E | Information Verified | Information Verified Sattisfactory. | Update 1 council resolution register and monitor implementation | Achived | N/A | N/A | (1) one updated council resolution register | Yes | F/M/Y/E/D | Satisfactory evidence a
FACILITIES
General Repairs and Maintenance Plan | Develop and maintain high quality municipal facilities | To review and implement General Repairs and Maintenance Plan | I7 | Number of General Maintanaince and Repairs plans aprroved | I7.1 | 2017/18 Repairs and Maintenance plan | 30516139 | OPEX | Develop one (1) council approved General Maintenance & Repairs Process Plan | Develop one (1) council approved General Maintenance & Repairs Process Plan | Achieved | N/A | N/A | Report on FM Plans and Annexure "A" | Yes | F/M/Y/E | Information Verified | Information Verified Sattisfactory. | N/A | N/A | N/A | N/A | N/A | N/A | N/A
|  |  |  | Number of General Maintanaince and Repairs plans reports produced | 17.2 | Four (4) 2017/18 Repairs and Maintenance Reports |  |  | Implement General Repairs and Maintenance Plan and report Quarterly | Implement General Repairs and Maintenance Plan and report | Achieved | N/A | N/A | Q1 Report on Municipal Buildings & Sites | Yes | F/M/Y/E | Information Verified | Information Verified Sattisfactory. | Implement General Repairs and Maintenance Plan and report | Achieved | N/A | N/A | Q2 Report on Municipal Buildings & Sites | Yes | F/M/Y/E/D | Information verified
FLEET MANAGEMENT
Fleet Management | Maintain High Quality Municipal Fleet | To manage and monitor Integrated Fleet Management operations | I8 | Number of Fleet Management plans approved | I8.1 | One (1) Fleet Management reports from the previous financial year | 4228662 | OPEX | Develop one approved Fleet Management Plan | Develop one approved Fleet Management Plan | Achieved | N/A | N/A | Report on FM Plans and Annexure "B" | Yes | F/M/Y/E | Information Verified | Information Verified Sattisfactory. | _ | N/A | N/A | N/A | N/A | Yes | F/M/Y/E/D
|  |  |  | Number of Fleet Management reports produced | I8.2 | Four (4) Fleet Management reports from the previous financial year |  |  | Implement Fleet management plan and report Quarterly | Implement Fleet management plan and report | Achieved | N/A | N/A | Q1 Report on Municipal Fleet Management & Repairs | Yes | F/M/Y/E | Information Verified | Information Verified Sattisfactory. | Implement Fleet management plan and report | Achieved | N/A | N/A | Q2 Report on Municipal Fleet Management & Repairs | Yes | F/M/Y/E/D | Information verified
INTERNAL PROTECTION SERVICES
Internal Protection Services | Provide Protection Services for public, employees and Councillors entering and using the municipality facilities and buildings | To safeguard the council assets, councillors and employees. | I9 | Number of crminal offenses within the municipality reduced (in relation to safeguarding of assets and employee security) | I9.1 | 10 incidents reported in the precious financial year (Five (5) break-ins and 5 tresspassing) | 20777780 | OPEX | Provide ongoing security services to the municipality and report quarterly | Provide ongoing security services to the municipality and report | Achieved | N/A | N/A | Q1 Report Annexure A (Protection Services Operational Status) | Yes | F/M/Y/E | Information Verified | Information Verified Sattisfactory. | Provide ongoing security services to the municipality and report | Achieved | N/A | N/A | Q2 Report Annexure A (Protection Services Operational Status) | Yes | F/M/Y/E/D | Information verified
SUMMARY
Total Mid-year Targets |  | 19
Targets Achieved |  | 18
Percentage Achievement |  | 95%

## TIE
SEDIBENG DISTRICT MUNICIPALITY
TRANSPORT, INFRASTRUCTURE AND ENVIROMENT - CUSTODIAN: EXECUTIVE DIRECTOR
PERFORMANCE REPORTING FOR 2018/19 FINANCIAL YEAR
Priority Area | IDP Strategy | IDP Objective | Objective No. | Key Performance Indicator (KPI) | KPI No: | Baseline | Budget Amount | Funding Source | Annual Target | Quarter One(1) | Achieved /Not Achieved | Reason for Non, under/Over Achievement | Corrective Action | POE Obtained | Mainstreaming Designated (Yes/No) |  | PMS Comments | Internal Audit Comments | Quarter Two(2) | Achieved /Not Achieved | Reason for Non, under/Over Achievement | Corrective Action | POE Obtained | Mainstreaming Designated (Yes/No) |  | PMS Comments
[15 empty] | (Yes/No) | Group F/M/Y/E/D | [7 empty] | (Yes/No) | Group F/M/Y/E/D
KPA 4: BASIC SERVICES AND INFRASTRUCTURE
TRANSPORT
Development of Integrated Transport Plan (ITP) | Plan and develop accessible, safe and affordable public transport systems and facilities. | To promote efficient and effective Integrated Service that addresses the socio-economic and environmental development imperatives of the region | G1 | Number of Integrated Transport Plan’s (ITP) developed and approves | G1.1 | Outdated Integrated Transport Plan (ITP) | R1,3m | Gauteng Department of Roads &Transport | Review Integrated Transport plan and submit to council for approval | _ | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Review Integrated Transport plan and submit to council for approval | Not Achieved | Document presented still lack information and consultation with stakeholders not done | The service providers are working on to close the gaps identified. | N/A | N/A | N/A | Satisfactory Evidence a
Airport | Implement Airport Turnaround Strategy | To provide self-sustainable airport services | G2 | Number of reports in Airpots Operations | G2.1 | New | 5664869 | OPEX | Monitor Operations of the airport and produce four reports | Monitor Operations of the airport and produce one report | Achieved | N/A | N/A | Report on Airport Operations | N/A | N/A | No POE | Airport Report not submitted to support the reported Achievement | Monitor Operations of the airport and produce one report | Achieved | n/a | n/a | Report on Airport Operations |  |  | Satisfactory Evidence a
INFRASTRUCTURE
Regional Infrastructure Projects | Plan for effective, efficient and sustainable infrastructural projects, water and sanitation services, and provision of electricity | To ensure effective delivery of infrastructure services | G3 | Number of Regional Infrastructure Projects monitored | G3.1 | Bi-annual reports per projects were tabled to council | 9144034 | OPEX | Monitor implementation of one (1) regional infrastructure project and report bi-annually | _ | Achieved | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Monitor implementation of one (1) regional infrastructure project and produce one report | Achieved | n/a | n/a | RRAMS and Regional Sewer reports |  |  | Satisfactory Evidence a
Rural roads Asset Management System | Plan for effective, efficient and sustainable infrastructural projects, water and sanitation services, and provision of electricity | To ensure effective delivery of infrastructure services | G3.1 | [5 empty] | Monitor progress on development of Rural Roads Asset Management Ststem and report Quarterly | Monitor progress on development of Rural Roads Asset Management Ststem and report Quarterly | Achieved | N/A | N/A | Report and Monthly RRAMS Report as attachements | N/A | N/A | Information Verified | POE Insufficient. There is no report signed by the Executive Deirector | Monitor progress on development of Rural Roads Asset Management Ststem and report Quarterly | Achieved | N/A | N/A | Report and Monthly RRAMS Report as attachements | N/A | N/A | Satisfactory Evidence a
LICENSING
License Service Centers | Render effective, efficient and customer oriented licensing services in the region | To ensure effective delivery of licensing services | G4 | Number of reports on implementation of Licensing Services. | G4.1 | Four (4) reports in 2017/18 Financial year | 60339266 | Department of Roads & Transport/OPEX | Produce four reports on implementation of Licensing Services | Produce one report on implementation of Licensing Services | Achieved | N/A | N/A | Report on Licensing Services | N/A | N/A | Information Verified | Information Verified Sattisfactory. POE submmited sufficient. | Produce one report on implementation of Licensing Services | Achieved | n/a | n/a | Report on Licensing Services |  |  | Satisfactory Evidence a
ENVIROMENT
Air Quality | Implementation of effective environment management in the Sedibeng District | To promote efficient and effective Integrated Service that addresses the socio-economic and environmental development imperatives of the region | G5 | Number of reports on Ambient Air Quality monitoring station | G5.1 | No Air Quality Management Plan | 24875190 | OPEX | Produce four report on Ambient Air Quality monitoring stations | Produce one report on Ambient Air Quality monitoring stations | Achieved | N/A | N/A | Report on Air Ambient Monitoring Stations | N/A | N/A | Information Verified | Information Verified Sattisfactory. POE submmited sufficient. | Report on ambient Air monitoring stations | Achieved | n/a | n/a | october, november and december reports on monitored stations |  |  | Satisfactory Evidence a
Environmental Awareness |  |  | G6 | Number of Environmental Awareness Campaigns | G6.1 | Four (4) Campaigns on 2017/18 |  |  | Conduct Four (4) Environmental Awareness Campaigns | Conduct one (1)) Environmental Awareness Campaign | Acheievd | N/A | N/A | Attandance Register | N/A | N/A | Information Verified | Information Verified Sattisfactory. POE submmited sufficient. | Conduct one (1)) Environmental Awareness Campaign | Achieved | n/a | n/a | Report on Provincial ARBOR DAY and attendance register |  |  | Satisfactory Evidence a
Municipal Health Services | Ensure a safe and healthy environment for people to live and work in and reduce environmental health risk | To promote efficient and effective Integrated Service that addresses the socio-economic and environmental development imperatives of the region | G7 | Percentage of compliance to Municipal Health Norms and Standards | G7.1 | 88% Compliance Achieved in 2017/2018 |  |  | Render Municipal Heath Services at 50% compliance with National Health Norms and Standards and report | _ | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | _ | N/A | N/A | N/A | Report on rendering of municipal health services | N/A | N/A | N/A
Targets Achieved |  | 11
Percentage Achievement |  | 91%

## SPED.
SEDIBENG DISTRICT MUNICIPALITY
STRATEGIC PLANNING AND ECONOMICC DEVELOPMENT - CUSTODIAN - EXECUTIVE DIRECTOR
PERFORMANCE REPORTING FOR 2018/19FINANCIAL YEAR
Priority Area | IDP Strategy | IDP Objective | Objective No. | Key Performance Indicator (KPI) | KPI No. | Baseline | Budget Amount | Funding Source | Annual Target | Quarter One(1) | Achieved /Not Achieved | Reason for Non, under/Over Achievement | Corrective Action | POE Obtained | Mainstreaming Designated (Yes/No) |  | PMS Comments | Imternal Audit Comments | Quarter Two(2) | Achieved /Not Achieved | Reason for Non, under/Over Achievement | Corrective Action | POE Obtained | Mainstreaming Designated (Yes/No) |  | PMS Comments
[15 empty] | (Yes/No) | Group F/M/Y/E/D | [7 empty] | (Yes/No) | Group F/M/Y/E/D
KPA 2: LOCAL ECONOMIC DEVELOPMENT
INTEGRATED DEVELOPMENT PLAN (IDP)
GDS III | Consolidate, Review and monitor Growth and Development Strategy (GDS | To co-ordinate the implementation of Regional Growth and development strategy | E1 | Number of Reports on Growth and Development Strategy | E1.1 | 2017/2018 Progress report on GDS III | 2247965 | OPEX | Produce Four (4) reports on Growth and Development Strategy | Produce one (1)report on Growth and Development Strategy | Not Achieved | The consultant is busy with the Growth and Development Strategy. | Progress report will be reported in Q2 | N/A | N/A | N/A | Not Achieved | Target Not Achieved | Monitor Progress on Growth and Development Strategy Flagship projects III and report | Achived | N/A | N/A | Councill Resolution | N/A | N/A | Satisfactory Evidence a
IDP | Coordinate developmentally–oriented municipal planning | To determine and plan for the developmental needs of the people of Sedibeng District Municipality | E2 | Number of Integrated Development Plans developed | E2.1 | 2017/2018 IDP |  |  | Develop one (1) approved IDP | Develop one (1) IDP Process Plan and submit to council for approval | Achieved | N/A | N/A | Council Resolutions and Approved IDP Process Plan 2018/19 | N/A | N/A | Information Verified | Information Verified Sattisfactory. | _ | N/A | N/A | N/A | N/A | N/A | N/A | N/A
DEVELOPMENT PLANNING AND HUMAN SETTLEMENTS
Development of Spatial Development Framework | Assessment of sector development plan and strategies | To ensure coherent strategic planning through Spatial Development Framework (SDF) | E3 | Number of sector development plans and strategies aligned to IDP | E3.1 | 1 Spatial Development Framework adopted in 2015 2017/18 SDF | 3660335 | OPEX | Review one SDF and submit to council for approval | _ | N/A | N/A | N/A | N/A |  |  | N/A | N/A | _ | N/A | N/A | N/A | N/A
Housing and Urban Renewal programme | Promote Urban Renewal and modernize urban develoment | To redress the spatial distortions of the Region | E4 | Housing and urban renewal programmes coordinated and delivered in 2018/19 financial year | E4.1 | Housing and urban renewal programmes coordinated in the previous financial year |  |  | Coordinate and monitor the implementation of housing and urban renewal programmes and report quarterly | Monitor and coordinate the implementation of housing and urban renewal programmes and report | Achieved | N/A | N/A | Report on Housing and Urban Renewal | Yes | F/M/Y/E | Information Verified | Information Verified Sattisfactory. | Monitor and coordinate the implementation of housing and urban renewal programmes and report | Achived | N/A | N/A | Report on Housing and Urban Renewal | Yes | F/M/Y/E | Satisfactory Evidence a
Regional Southern Corridor Projects reporting. | To assist the Region to address past spatial imbalances and land-use management | Promote Regional Economic Development | E5 | Number of reports on the implementation plans of Regional Southern Corridor Projects | E5.1 | Southern Corridor Regional Implementation Plan. |  |  | Co-ordinate the Implementation of the Southern Corridor Regional Implementation Plan and produce four reports | Co-ordinate the Implementation of the Southern Corridor Regional Implementation Plan and produce one report | Achieved | N/A | N/A | Report on Southern Corridor Implementation | Yes | F/M/Y/E | Information Verified | Information Verified Sattisfactory. | Co-ordinate the Implementation of the Southern Corridor Regional Implementation Plan and produce one report | Achived | N/A | N/A | Report on Southern Corridor Implementation | No |  | Satisfactory Evidence a
SPLUMA Implementation | To assist the Region to address past spatial imbalances and land-use management | To provide inclusive developmental, equitable and efficient spatial planning of the Region | E6 | Number of reports on implementation of SPLUMA in the Region | E6.1 | SPLUMA |  |  | Coordinate the Implementation of SPLUMA in the region and produvr four reports | Coordinate the Implementation of SPLUMA in the region and report | Achieved | N/A | N/A | Report on SPLUMA implementation | Yes | F/M/Y/E | Information Verified | Information Verified Sattisfactory. | Coordinate the Implementation of SPLUMA in the region and report | Achived | N/A | N/A | Report on SPLUMA implementation | No |  | Satisfactory Evidence a
LOCAL ECONOMIC DEVELOPMENT
EPWP | Creating work opportunities in public social programmes | To create decent work & sustainable livelihoods, education, health; rural development; food security & land reform.To promote local economic opportunities | E8 | Number Expanded Public Works Program (EPWP) beneficiaries employed | E8.1 | Hundred and twenty-two (122) EPWP beneficiaries employed in the previous financial year | 6366156 | OPEX/EPWP Grant | Employ 100 EPWP beneficiaries | _ | N/A | N/A | N/A | N/A |  |  | N/A | N/A | Employ 100 EPWP beneficiaries | Not Achieved | The budget allocation only covered 94 beneficiaries | Monicipality is still Lobbying more funds for this target | Report Payroll List of EPWP Participants | Yes | F/M/Y/E | Satisfactory Evidence a
SMME and Cooperatives Development | Ensure that adequate financial and non-financial assistance is provided to SMMEs and Cooperatives |  |  | Number of SMMEs and Cooperatives capacitated | E8.2 | 50 Cooperatives and SMME's trained in the previous financial year |  |  | Co-ordinate Capacitation and support 30 SMME’s and Cooperatives (including small scale farmers) and produce four (4) reports | Provide support to fifteen (5) SMMEs and Cooperatives and produce one report | Achieved | Target Over-archieved due to availability of resources from sector departments | N/A | Attendance Registers | YES | F/M/Y/E | Information Verified | Information Verified. | Provide Support to ten (10) SMMEs and Cooperatives and report | Achieved | Target Over-archieved due in Quarter one. 20 SMME and Co-ops owners Trained | N/A | Peport,Programme for the event and Attendance Registers | Yes | F/M/Y/E | Satisfactory Evidence a
TOURISM
Tourism Demand | Participation in Provincial marketing initiatives | To create Tourism demand in the region | E9 | Identify and participate in 4 marketing initiatives | E9.1 | Participated in Four Tourism Initiatives in the previous financial year | 3185993 | OPEX | Identify and participate in one (1) Markrting and Tourism initiative and produce one report | _ | N/A | N/A | N/A | N/A | N/A | N/A | Information Verified | Information Verified Sattisfactory. | Market Sedibeng Regional Tourism through participation on provincial marketing initiatives and report | Achieved | N/A | N/A | Report on Regional Tourism | Yes | F/M/Y/E | Satisfactory Evidence a
Tourism Supply | Development of product and skills in the tourism industry | To promote and Develop Tourism | E10 | 4 Skills development and tourism awareness programmes facilitated. | E10.1 | 120 Tourism Students trained. Quality of tourism products and services in the region not on the required level. |  |  | Facilitate four (4) skills development and tourism awareness programmes and report | Facilitate one (1) skills development and tourism awareness programme and report | Achieved | N/A | N/A | Report and Attendance register | N/A | N/A | Information Verified | Information Verified Sattisfactory. | Facilitate one (1) skills development and tourism awareness programme | Achieved | N/A | N/A | Report and Attendance register | Yes | F/M/Y/E | Satisfactory Evidence a
FRESH PRODUCE MARKET
Fresh Produce Market | To provide a central market distribution system for the region and maximize municipal revenue | To provide efficient services to local suppliers and buyers | E11 | Number of Fresh Produce Market reports submitted to council | E11.1 | Four (4) Fresh Produce Market Strategy | 10424607 | OPEX | Produce four (4) Fresh Produce Market Reports and submit to council | Produce one (1) Fresh Produce market Reports and submit to council | Achived | N/A | N/A | Report on Fresh Produce Market | N/A | N/A | Information Verified | Information Verified Sattisfactory. | Produce one (1) Fresh Produce market Reports and submit to council | Achieved | N/A | N/A | Report on Fresh Produce Market | N/A | N/A | Satisfactory Evidence a
MID-YEAR PERFORMANCE SUMMARY
Total Mid-year Targets |  | 17
Targets Achieved |  | 15
Percentage Achievement |  | 88%

## Community Services
SEDIBENG DISTRICT MUNICIPALITY
COMMUNITY SERVICES - CUSTODIAN: EXECUTIVE DIRECTOR
PERFORMANCE REPORTING FOR 2018/19 FINANCIAL YEAR
Priority Area | IDP Strategy | IDP Objective | Objective No: | Key Performance Indicator | KPI No. | Baseline | Budget Amount | Funding Source | Annual Target | Quarter One(1) | Achieved /Not Achieved | Reason for Non, under/Over Achievement | Corrective Action | POE Obtained | Mainstreaming Designated (Yes/No) |  | PMS Comments | Internal Audit Comments | Quarter Two(2) | Achieved /Not Achieved | Reason for Non, under/Over Achievement | Corrective Action | POE Obtained | Mainstreaming Designated (Yes/No) |  | PMS Comments
[15 empty] | (Yes/No) | Group F/M/Y/E/D | [7 empty] | (Yes/No) | Group F/M/Y/E/D
KPA 4: BASIC SERVICES AND INFRASTRUCTURE
COMMUNITY SAFETY
Community Safety Programmes | To implement community safety programmes | To promote and build safer communities | H1 | Number of Community Safety Programmes implemented | H1.1 | 2017/18 Community safety Reports | 6821415 | OPEX | Implement twelve (12) Community Safety Programmes and report | Implement four (4) Community Safety Programmes and report | Achieved | N/A | N/A | Signed Report, Agenda, attandance Register and Minutes |  |  | Information Verified | Information Verified Sattisfactory. POE submmited sufficient. | Implement four (4) Community Safety Programmes and report | Achieved | N/A | N/A | Report, Agenda, attendance Register and Minutes | Yes | All | Evidence Satisfactory a
DISASTER MANAGEMENT
Disaster management awareness | To conduct community awareness campaigns | To promote disaster resilient communities | H2 | Number of Disaster Management awareness programmes conducted | H2.1 | Four (4) Awareness campaigns in 2017/18 | 10831616 | OPEX | Conduct four (4) Public Disaster Management awareness programmes and report | Conduct one (1) Public Disaster Management awareness programmes and report | Achieved | N/A | N/A | Attandance Register |  |  | Information Verified | Information Verified Sattisfactory. POE submmited sufficient. | Conduct one (1) Public Disaster Management awareness programmes and report | Achieved | N/A | N/A | Yes, Attendance Register and Pictures | Yes |  | Evidence Satisfactory a
HEALTH AND SOCIAL DEVELOPMENT
District Health Council Activities | Promote the efficient delivery of Primary Health Care | To ensure effective Service Delivery | H3 | Number of Primary Health Care (PHC) Programmes implemented | H3.1 | Three (3) District Health Council Meetings 0n 2017/18 financial year |  | OPEX | Coordinate three (3) District Health Meetings | Coordinate one (1) Dstrict Health Meetings | Achieved | N/A | N/A | Report and Attendance Register |  |  | Information Verified | Information Verified Sattisfactory. POE submmited sufficient. | _ | N/A | N/A | N/A | N/A | N/A | N/A | Evidence Satisfactory a
Women and Gender Programmes | Encourage women to take charge of their lives | To provide women empowerment platforms | H4 | Number of Women and Gender Programmes implemented | H4.1 | Three (3) Women and Gender Programmes in 2017/18 Financial year |  |  | Conduct three (3) Women and Gender Programmes | Conduct one (1) Woment and Gender programme and report | Achieved | N/A | N/A | Report and Attendance Register |  |  | Information Verified | Information Verified Sattisfactory. | Conduct one (1) Woment and Gender programme and report | Achieved | N/A | N/A | Women and Gender Report and Attendance Register |  |  | Evidence Satisfactory a
SPORTS, ARTS & CULTURE
Sports and Recreation Programmes | Provide developmental Sports, Arts and Cultural Programs | To improve their quality of lives for the people of the region | H8 | Number of Sports development programmes coordinated | H8.1 | Four (4) Programmes in the previous financial year | 14482546 | OPEX | Coordinate (4) Developmental Sports Programmes and Consolidation of the Approved Regional Recreation Policy with GP SACR | Coordinate one (1) Developmental Sports Programmes and Consolidation of the Approved Regional Recreation Policy with GP SACR | Achieveed | N/A | N/A | Attandance register and photos of the event |  |  | Information Verified | POE not sufficient | Coordinate one (1) Developmental Sports Programmes and Consolidation of the Approved Regional Recreation Policy with GP SACR | Achieved | N/A | N/A | SRAC &H Report, Attendance Register and Posters | Yes | All | Evidence Satisfactory a
Arts and Culture Programmes |  |  |  | Number of Arts and Cultural programmes coordinated | H8.2 | Four (4) Programmes in the previous financial year |  |  | Coordinate Four (4) Arts and Culture Programmes and Two (2) Craft Hub Programmes | Coordinate One (1) Arts and Culture Programme and Two (2) Craft Hub Programmes | Achived | N/A | N/A | Attandance register |  |  | Information Verified | POE not sufficient | Coordinate One (1) Arts and Culture Programme and report | Achieved | N/A | N/A | SRAC &H Report, Attendance Register and Posters | Yes | All | Evidence Satisfactory a
Targets Achieved |  | 11
Percentage Achievement |  | 100%